## Sheet1
TASK | MONTH
Development of calibration using Bayesian optimization | YEAR | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
1
2
3
4
Implementation of Orthogonal Additive Kernels | 1 | bar: M5 to M12
2
3
4
Implementation of constraints in Bayesian Optimization | 1
2 | bar: M1 to M8
3
4
Test and validation of calibration on simplified lung model | 1 | bar: M4 to M10
2
3
4
Test and validation of calibration on endometrium model | 1 | bar: M9 to M12
2 | bar: M1 to M8
3
4
Test and validation of calibration on external model | 1
2 | bar: M5 to M12
3
4
Conference submissions and presentations | 1 | bar: M2 to M3; M9 to M10
2 | bar: M1 to M2; M9 to M10
3
4
Manuscript submissions and publications | 1 | bar: M8 to M12
2
3
4
Thesis writing and defense | 1
2
3
4 | bar: M5 to M12

## Sheet2
TASK | MONTH
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Development of calibration using Bayesian optimization
Implementation of constraints in Bayesian Optimization | bar: MONTH M1 to MONTH M8
Test and validation of calibration on endometrium model | bar: MONTH M1 to MONTH M8
Test and validation of calibration on external model | bar: MONTH M5 to MONTH M12
Dissemination | MONTH M1: CCIA 2023; MONTH M9: PhD Consortium
TASK | MONTH M1: MONTH
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Development of calibration using Bayesian optimization
Implementation of Orthogonal Additive Kernels | bar: MONTH M5 to MONTH M12
Test and validation of calibration on simplified lung model | bar: MONTH M4 to MONTH M10
Test and validation of calibration on endometrium model | bar: MONTH M9 to MONTH M12
Dissemination | MONTH M2: PhD Day; MONTH M9: PhD consortium